## Sheet1
2018-09-26 |  |  |  | Updated: 5/4/2017
PN 1234567-001 |  |  | LOT 1 | LOT 2 | LOT 3 | LOT 4 | … | … | … | … | … | … | … | …
LM - Contract Date |  |  | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
Priority
Days late to contract vs. planned date |  |  | -2 | 12 | 26 | 40
# of parts in batch |  |  | 20 | 20 | 20 | 20
# of parts shipped |  |  | 0 | 0 | 0 | 0
# of parts remaining |  |  | 20 | 20 | 20 | 20
Actual Days Late to Contract | [6 empty] | 0
PLANNED SHIP DATE
PROCESS | SPAN (Days) |  | 2017-10-16 | 2017-10-30 | 2017-11-13 | 2017-11-27
0
0
Ship | - |  | 2017-10-16 | 2017-10-30 | 2017-11-13 | 2017-11-27
Stamp & Final QA | 3 |  | 2017-10-13 | 2017-10-27 | 2017-11-10 | 2017-11-24
Insert Set Screws | 4 |  | 2017-10-09 | 2017-10-23 | 2017-11-06 | 2017-11-20
Inspection | 7 |  | 2017-10-02 | 2017-10-16 | 2017-10-30 | 2017-11-13
Outside Thermal Treat | 7 |  | 2017-09-25 | 2017-10-09 | 2017-10-23 | 2017-11-06
Coating | 7 |  | 2017-09-18 | 2017-10-02 | 2017-10-16 | 2017-10-30
Diamond Turn | 21 |  | 2017-08-28 | 2017-09-11 | 2017-09-25 | 2017-10-09
Thermal Cycle | 4 |  | 2017-08-24 | 2017-09-07 | 2017-09-21 | 2017-10-05
Chromate | 4 |  | 2017-08-20 | 2017-09-03 | 2017-09-17 | 2017-10-01
Lap Back | 14 |  | 2017-08-06 | 2017-08-20 | 2017-09-03 | 2017-09-17
Procure Materials | 84 |  | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
PO Review | 2 |  | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
***NOTE: PROCESSES INCLUDE CLEANING & IN-PROCESS INSPECTION***
Weeks to complete |  | 24 |  |  | TOTAL PARTS ON ORDER |  | 74
Parallel Days |  | 0
Cycle Time |  | 168 |  |  | TOTAL PARTS SHIPPED |  | 0
Serial days |  | 157 |  |  | TOTAL PARTS REMAINING |  | 74
***Based on calendar days***
Legend
Operation Complete |  | Parallel Operations
Work Stopped |  | Serial Operations
Rework |  | FRB
Work in Process |  | MRB